## Modules_Back
index		Feature Name	role	Status	Priority	dependency	Version	WEB	Test	Start	End	Developer	User Journey	Description	URL	implementation	Comments	User Journey
0		Register												User will register by their.
1		Profile	private									ABEDEEN
2		Photo						BF				ABEDEEN
3		Change Photo						BF				ABEDEEN
4		Read Photo	public					BF				ABEDEEN
5		Basic						BF				ABEDEEN		The basic information if a user. The information will be loaded when a user will successfully logged in.
6		create						BF	y			ABEDEEN
7		update						BF	y			ABEDEEN
8		delete						BF	y			ABEDEEN		To delete any field have to keep the field empty.
9		load	public					BF	y			ABEDEEN		After successful login the data will be loaded from automatically
10		About						BF	y			ABEDEEN
11		create						BF	y			ABEDEEN
12		update						BF	y			ABEDEEN
13		delete						BF	y			ABEDEEN		no separate delete for it, just keep the field empty.
14		load	public					BF	y			ABEDEEN
15		Education						BF	y			ABEDEEN
16		create						BF	y			ABEDEEN
17		update						BF	y			ABEDEEN
18		delete						BF	y			ABEDEEN
19		load all	public					BF	y			ABEDEEN
20		Jobs						BF	y			ABEDEEN
21		create						BF	y			ABEDEEN
22		update						BF	y			ABEDEEN
23		delete						BF	y			ABEDEEN
24		load all	public					BF	y			ABEDEEN		All data will be back, in desired order on desired column.
25		pagination												from font end have to send pagination with request.
26		order by
27		order on												the name of the column
28		Search												Pagination & AnyKey. / It will be public. Any one can do a search among the members of the Alumni. / Like any student of the particular department can search for a senior for particular reason like skills, research interest.
29		Organization												Which organization the people is working.
30		Name												Both first Name and last Name
31		Role												Role in the company like : software engineer, web designer, data analytics etc.
32		skills												search will be done “any key search”
33		research interest
34		phone
35		email
36
37		Events												All the events will be kept there. Registration for the event can also be done from here.
38		Create	organization secretary					B
39		delete	organization secretary					B
40		update	organization secretary					B
41		load all	public					B
42		pagination
43		order by
44		order on
45		registration
46		cancel												one can able to cancel registration
47		confirm registration												the admin will confirm the registration after he/she received the payment. When admin/accountant will acknowledge that he/she got payment, registration will be confirmed.
48
49		Committee
50		Accounts												Later
51		Job Posting												Later
52		Role												Person with Admin role will able to see all the private information of a user. A url will be designed that admin will only able to use.
53		Commeiete												Have to option that admin can able to make commite. Option will be given that add role. Role description, add date. Admin can add member to the commite from exiting member list. And this admin account have to add from DB in DB admin. Account system can be added later.
54		Payments
55		Payment Type
56		create	accounts					BF				Sajib
57		update	accounts					BF				Sajib
58		delete	accounts					BF				Sajib
59		load all	user					BF				Sajib		All data will be back, in desired order on desired column.
60		pagination						BF				Sajib		from font end have to send pagination with request.
61		order by						BF				Sajib
62		order on						BF				Sajib
63		Payments
64		Mobile										Arif		the payments will be done by the mobile.	payment/mobile
65		create						B		12/05/19	12/05/19	Arif			../create
66		update						B		12/06/2019	12/06/2019	Arif		if a payment is approved by the admin, user means the payer will not able to update it any more. Have to sent update request.	../update
		find One						B		12/05/19	12/05/19	Arif			../findOne
67		delete						B		12/06/2019	12/06/2019	Arif		if a payment is approved by the admin, user means the payer will not able to delete it any more. Have to sent delete request.	../delete
68		payments by a user										Arif		The total mobile payments done by a user. User id will be get automatically.	../getallByUser
		getAll payments						B		12/06/2019	12/06/2019	Arif		to get all the payments. With pagination, sort on(column name, based on which sorting will be done), order by(Ascending/descending)	../getall
		getAll not approved methods												The mobile payments that yet approved.
		count
		total number of mobile payment										Arif		the total number mobile payments so far done.
		payment by certain operator										Arif		How many payments has done by using certain operator like bKash, Rocket etc… For say : among total of 1000 mobile payments 600 has done bKash, 300 by Rocket. By the request client will provide operator name, in response have to return total payment done by using this operator.
		Search
		mobile number												will back the total number payments done this mobile number.
		Type ID												means how many payments done for a certain payment type like : “picnic 2020” events has payment id 44, it will show all the payments done for this payments type id 44, for the event “picnic 2020”. have to provide pagination and sorting (means sorting can be done on date).
		count All												How many payments done. Just the count.

69		Accountant
70		approve/acknowledge
71		discard
74		On Cash
75		Other												Means all other kind of payment except the mobile of cash
76		MyPayments												it will show the total number of Payments a user has done. Here will be shown among this, how many have been approved and how many have been still pending.
77

## DataTables
Table Name	field Name	Type	Integrity / P= Public / P/P = means public or private and have to keep option to make it public or private	Description
User account				Student will register by their student ID and Password. Have to verify the information. Here have to chcek is it possible. Have to decide how to verify the information. Do we have any option to verify the information through any API or Not.
	Student ID
	Password
	Role

Profile
	First Name		P
	Last Name		P
	Gender		P
	ID		P
	batch		P
	Passing Year		P
	Contact No		P/P	Will be used to verify.
	Email Address		P	have to use verification. Cause any one mail alumni for any reason and as mail not bother people so it can be P. One can mobile or further contact information by mail.
	Work History		P/P
	Education Qualification		P/P
	Research Interest		P
	Present Address		P/P
	Permanent Address		P/P
	DoB		P/P
	Blood Group		P/P
	Mareterial status		P/P
	Home District		P	People will be see and find out their same UP people. It can be P for All.
	Skills		P
	Photo		P/P
	About Me		P/P	Use can express his personal view on something, can write the projects he is doing now, his/her achievment so on/
	Social Media Links
	religion

Profile_Basics

Work History	Will be one to many with Profile and Join Column with Student ID.
	ID(PK)
	Student ID(FK, JOIN COLUMN)
	Organization Name
	Organization Address
	Responsibility
	Join Date
	Leave Date			If still working then leave date NULL or WORKING
	type			P or P, organization. It is built as that it can be used by out of CSE people. And P and govt so that people can easily find out govt employee of the University.

Education Qualification				Will be one to many with Profile and Join Column with Student ID.
	ID (PK)
	Student ID(FK, JOIN COLUMN)
	Name of the Degree
	Passing Year
	Organization Name
	Organization Address

Payment_Mobile				People will able to see their payment history. For on cash payment, he have to wait to see the payment update.
	ID	BigInt
	Student_ID(FK, JOIN COLUMN)	BigInt		Means who have done the payment; user ID of the Current Logged User.
	Amount	number
	Type_ID	BigInt		Means for the payment is being done.
	Date	date		Current date can will be given or date when u send the payment.
	Amount	number		amount sent for payment.
	Payment Method	Varchar 512		Mobile Payment. On cash. Mobile operator name.
	Mobile Number	Varchar 512		The mobile number by which payment has been done.
	Trx ID	Varchar 512		For Mobile Payment.
	Status	number		For Mobile Payment user will send the money through mobile and wait for the payment be received. When payment will be received a SMS will be sent to his given mobile number.
Payment_Other
	ID
	student ID
	payment_type
	amount
	Description

Payment Type				Like Membership fee, Any seminar fee, Ifftar Maffil fee, pinic fee etc. it can be later edited and added.
	ID(PK)
	Name
	Description
	Last Date
	Amount

	0
Event
0	ID	BigInt		Auto Increment
1	user_id	BigInt		who is creating the event means the current user.
2	Title of the event	Varchar 512
3	Start Date	Date		date
4	End date	date
5	Fee	number
6	Location	Varchar 512
7	Description	meduimText
8	Notes	meduimText
9	Images			First have to upload the images separately then can be added as link.

Posts	That can be used for any news and jobs etc.
	ID
	Date
	content

Social Media Links

Division
District
Upzilla